## 1. INSTRUCTIONS
INSTRUCTIONS
This is the first of five sheets in this Excel workbook. This first sheet contains instructions for completing the tracker, the second sheet contains the fillable project tracker sheet. The third sheet contains the fillable financial summary sheet, and the fourth and fifth sheets contain examples of the Project Tracker and Financial Summary.
1) Open the "PROJECTS" worksheet (second tab) highlighted in blue and complete the following:
a) This sheet is prepopulated with information from the state’s previously submitted Project Trackers (e.g. 2022), as well as information from CMS Location on recently approved projects. Review the "prepopulated projects" for accuracy and provide updates, as necessary. Please specify any changes in Column M. Additionally, states are required to provide either interim or final project results, as appropriate, in Column J, see below for directions. b) Add any missing projects on a new row and complete all required fields for the "added projects".
State (Column A) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, this field should only be populated with the value that is available in the drop-down selection.
CMS Location (Column B) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, this field should only be populated with the value that is available in the drop-down selection.
Unique Identifier (Column C) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, this field should only be populated with the identifier provided by CMS. Please provide a copy of the CMS approval letter for any projects added to the spreadsheet. c) If adding a continuation or extension project, please enter the project into a separate row with it's assigned UID. DO NOT enter information into the same row as the original project used as the model for the continuation or extension.
Project Start Date (Column D) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) Enter the start date of the project (i.e., the date that funding started). DO NOT enter the date the project was approved for funding. The project may have been approved months before funding began; only enter the date when the funding officially started. Please follow the format (MM/DD/YYYY). Example: 06/10/2022. If the specific date is not known, use the first of the month: 06/01/2022.
Project End Date (Column E) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) Enter the end date of the project. Whenever possible, please include specific dates, not just the month and year. Please follow the format (MM/DD/YYYY). Please indicate in Column M if the project was approved to receive a no-cost extension due to the impacts of the COVID-19 Pandemic on the project activities. Example: 09/25/2022 If the specific date is not known, use the first of the month: 10/01/2022.
Total Amount of CMP Funds Approved for this Project (Column F) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, please add the total amount from the CMS project approval letter.
Project Title (Column G) a) For prepopulated projects, this field is locked for editing. If correction is required, please add a note in Column M. b) For added projects, please add the Project Title from the CMS project approval letter.
Project Summary (Column H) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, enter the following project summary information: a) Specific purpose of the project; b) Description of project's measurable goals and/or objectives; c) Explanation of how the project will benefit nursing home (NH) residents; b) Target audience beyond NH residents (i.e., NH staff, caregivers, family councils), if applicable. Please follow the format in the example below. Project ABC's Creative Storytelling will train and certify 50 nursing homes in improvisational storytelling to reduce challenging behaviors and antipsychotic medication use by 10%. c) In addition to improving communication, social connectedness the project will facilitate positive engagement between staff and residents. d) 50 nursing homes in the state. c) Please indicate if the project is an extension or a continuation of a previously approved CMP project.
Funded Entities (Column I) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, list each entity that will directly receive CMP funds for this project (i.e., if funds are being given directly to a nursing home, or non-nursing home entity such as an individual consultant, vendor, or academic institution, please list the name of the entity). DO NOT include the names of subcontracted entities. Example: Project ABC Creative Storytelling, Inc.
Results/Outcomes of the Project (Column J) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. Final project results must be entered for all projects that have been completed. Interim project results must be entered for all ongoing projects. b) For added projects, describe the project's interim or final results and outcomes of the project. Include a brief summary of the specific goals that were met/not met, as well as any other benefits resulting from the project. Reference quantitative measures that reflect goals of the project. If the project is ongoing after the date in which the state submits the Project Tracker, indicate "Results Pending" in Column J. Example: Project ABC recruited 50 nursing homes to engage in training for the ABC program to improve resident communication and social connectiveness. The project outcomes show a 10% reduction in residents exhibiting signs or symptoms of depression, challenging behaviors, and use of antipsychotic medication as well as a 20% in enjoyment of activities and social interaction.
Total Amount of CMP Funds Expended During CY 2021 (Column K) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, enter the total amount expended during CY 2021. If this is a multi-year project or a project that is one year or less but spans multiple years (e.g., 11/05/2019 - 11/04/2022), please enter the funds that were used during calendar year 2021. Example: $50,000.00
Total Amount of CMP Funds Expended During CY 2022 (Column L) a) For prepopulated projects, this field is unlocked for editing. Please edit, as necessary and add a note in Column M indicating that a change has been made. b) For added projects, enter the total amount spent on this project during CY 2022. If this is a multi-year project or a project that is one year or less but spans multiple years (e.g., 11/05/2019 - 11/04/2022), please enter the funds that were used during calendar year 2022. Example: $50,000.00
Notes (Column M) Please use this column to request changes to information in the prepopulated rows for the columns that are locked for editing. Any other data in the notes column will not be included in the final Project Tracker on the CMPRP webpage.
2) Open the "FINANCIAL_SUMMARY” worksheet (third tab) highlighted in orange and complete the following:
a) The state must add information to all four highlighted fields on this tab. Failure to provide this information will result in the file being returned to the state. If the total amount is zero, enter "$0." b) Validate financial information highlighted in blue, which is described below.
CMP Funds Balance as of 01/01/2022 (Obligated and Available) (Column B) Enter the amount that was obligated and available for use as of 01/01/2022 for the state.
CMP Funds Expended for Administrative Uses in CY 2022 (Column C) Enter the actual amount of CMP funds spent for administration in 2022.
CMP Funds Expended for Emergency Uses in CY 2022 (Column D) Enter the actual amount of CMP funds spent for emergencies in 2022.
CMP Funds Added During CY 2022 (Column F) Enter the actual amount of CMP funds that were added to the state's total balance in 2022. Note that the state was required to report the anticipated CMP funds returned to the state in 2022 as part of the CY2023 State Plan submission process.
CMP Funds Spent During CY 2022 on CMP Projects (Column E) This cell will auto-populate with the total amount of CY 2022 funds listed in the projects from tab 3, "PROJECTS," Column L.
CMP Funds Balance as of January 1, 2023 (Column G) This cell will auto-calculate by subtracting expended administrative, emergency and project funds from the CMP Funds Balance as of 01/01/2022, and adding CMP funds added during CY 2022. This balance will not include funds expended from Communicative Technology (CT) or Visitation Aid (VA) applications.
3) Save and send the Project Tracker spreadsheet to the CMPRP mailbox (CMP-Info@cms.hhs.gov) by 02/1/2023
*Please reach out to the CMPRP Team with any questions by contacting the mailbox at: CMP-Info@cms.hhs.gov

## 2. PROJECTS
FILLABLE TRACKER
Tracker Calendar Year (CY)
State | CMS Long-Term Care Location | Unique Identifier | Project Start Date (Please review and edit the values in this field, as applicable) | Project End Date (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Approved for this Project | Project Title | Project Summary (Please review and edit the values in this field, as applicable) a) Specific purpose of the project b) Description of what the project will achieve c) Explanation of how the project will benefit nursing home (NH) residents d) Target audience beyond NH residents, if applicable | Funded Entities (Please review and edit the values in this field, as applicable) | Results/Outcomes of the Project (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Expended on Projects During CY 2021 (Please review and edit the values in this field, as applicable) | Total Amount of CMP Funds Expended on Projects During CY 2022 (Please review and edit the values in this field, as applicable) | Notes (Please add an applicable information upon your review)
MT | Denver | MT-0619-BH-320 | 2019-09-01 | 2022-08-31 | 40796 | In Someone Else's Shoes - A Geriatric Empathy Project | The applicant aims to improve resident care by educating their nursing staff on the physical limitation residents face. This includes helping staff to understand how the surrounding environment is seen, felt, and interpreted due to age-related changes in sensory input, especially sight, hearing, touch, and movement. The proposed training will be implemented over the course of a two-year period. The project was granted a no-cost extension through 8/31/2022 due to the impacts of the COVID-19 pandemic. | Benefis Hospitals, Inc. | 16 Empathy trainings were done over eight months. 42 staff participated in the training. Training was limited due to the Pandemic and staffing shortages, but 100 percent of the attendees to the training indicated a high level of satisfaction with the training and are more aware of the struggles of agina dn more empathetic to the residents. Staff are now more able to improve patient care due to the Empathy training | 0 | 4300
MT | Denver | MT-1219-BH-501 | 2020-04-01 | 2023-03-31 | 6384 | Reverie Harps to Promote Healing and Relaxation for Nursing Home Residents | This project will provide easy-to-use harps in three nursing homes for resident use. Reverie harps are easy to use and provide soothing, therapeutic music for residents. The project will ensure staff are trained on the harp program’s benefits and the harps’ use. | Benefis Hospitals, Inc. | Pending | 0 | 4483 | Project not complete yet.
MT | Denver | MT-1219-BIA-503 | 2020-04-01 | 2023-03-31 | 150000 | Brain Injury Training for Nursing Home Support Staff and Health Professionals | The project will provide training for nursing facility staff based on a specialty care curriculum on brain injury awareness, support and prevention. The curriculum will include an introduction to traumatic brain injury (TBI), communication, promoting skills for independence, understanding and managing cognitive and behavior changes following a TBI, and working with families after a TBI. The training will include in person classes held quarterly and online classes held bi-monthly, for a minimum of 10 session per year. The training will provide direct improvements to resident’s quality of care and provide staff knowledge to reduce stress, frustrations and turnover. | Brain Injury Alliance | Pending | 81222.88 | 49983 | Project not complete yet.
MT | Denver | MT-0820-AA-654 | 2020-05-01 | 2023-03-31 | 380689 | Dementia Care Practice Recommendations: Organization-Wide Coaching and Implementation in Montana | The project will provide person-centered dementia care practices that have shown significant effects of decreasing behavioral symptoms and psychotropic medication use in residents with dementia in long-term care. Person-centered care practices also lead to positive effects for residents with regard to quality of life, decreased agitation, improved sleep patterns, and maintenance of self-esteem. Additionally, staff-related benefits of person-centered care models include reduction in stress, burnout and job dissatisfaction, which may also lead to reduced staff turnover - a significant challenge within long-term care. These results also found that person-centered practices and culture change principles were related to both better quality of life for residents with dementia and better working conditions for staff. Nursing homes will be able to focus on areas that are most important to them or have been cited for; through the collaboration with the coach, nursing homes will be able to set priorities based on their specific needs. | Alzheimer's Association | Pending | 56849.41 | 218765.98 | Project not complete yet.
MT | Denver | MT-0820-WCNH-658 | 2021-05-01 | 2022-04-30 | 10155.62 | Outdoor Playground Fun and Technology Expansion Project | This project is intended to promote independence and reduce unwanted behaviors, expand technology for resident communication with family as well as expand the Music and Memory equipment, and implement fun outdoor activities for the residents. | Wibaux County Nursing Home | Program was requested for only one year. First year was purchase of equipment and learning, project was complete as of April 30, 2022 in which a final report was sent. Results were that the playground equipment improved mood and enriched residents lives, but did not see a change to the residents quality of measure of s/sx depression. However, residents continue to use the games and activities with families and do still enjoy the time spent. | 9841.39 | 0

## 3. FINANCIAL_SUMMARY
FILLABLE FINANCIAL SUMMARY TRACKER
Tracker Calendar Year (CY)
State | CMP Funds Balance as of January 1, 2022 (Obligated & Available) | CMP Funds Expended for Administrative Uses in CY2022 | CMP Funds Expended for Emergency Uses in CY2022 | CMP Funds Spent on Projects in CY2022 | CMP Funds Added in CY2022 | CMP Funds Balance as of January 1, 2023
MT | 670157.98 | 6911.21 | 14003.6 | 277531.98 | 255335.27 | 627046.46

## 4. EXAMPLE_PROJECTS
EXAMPLE TRACKER
Tracker Calendar Year (CY) |  | 20XX
State | CMS Long-Term Care Branch | Unique Identifier | Project Start Date | Project End Date | Total Amount of CMP Funds Approved for this Project | Project Title | Project Summary a) Specific purpose of the project b) Description of what the project will achieve c) Explanation of how the project will benefit nursing home (NH) residents d) Target audience beyond NH residents, if applicable | Funded Entities | Results/Outcomes of the Project | Total Amount of CMP Funds Expended During the Calendar Year | Total Amount of CMP Funds Expended During the Calendar Year | Notes
OH | Chicago | XXXX-OH-XXX | 1/1/20XX | 12/31/20XX | 50000 | TimeSlips Creative Storytelling | a) The purpose of this project is to improve communication and social connectedness for nursing home residents. b) TimeSlips Creative Storytelling will train and certify 50 nursing homes in improvisational storytelling. They will recruit and train facility staff, certify lead facilitators, and hold face-to-face and virtual coaching sessions for technical assistance. c) In addition to improving communication and social connectedness, the project aims to reduce challenging behaviors, reduce antipsychotic medications, and encourage positive engagement between staff and residents. d) 50 nursing homes in the state. | TimeSlips Creative Storytelling | TimeSlips recruited 50 nursing homes to engage in training for the Creative Storytelling program. Survey responses collected from all 50 nursing homes showed a 20% reduction in resident depression, irritability, and apathy as well as a 30% increase in enjoyment of activities and social interaction. A total of 49 testimonials detailing resident improvement in imagination/ creativity, community contribution, talking, and laughing serve as strong qualitative indicators of success. | 0 | 30000 | N/A

## 5. EXAMPLE_FINANCIAL_SUMMARY
EXAMPLE FILLABLE FINANCIAL SUMMARY TRACKER
Tracker Calendar Year | 20XX
State | CMP Funds Balance as of January 1, 20XX (Obligated & Available) | CMP Funds Expended for Administrative Uses in CY20XX | CMP Funds Expended for Emergency Uses in CY20XX | CMP Funds Spent on Projects in CY20XX | CMP Funds Added in CY20XX | CMP Funds Balance as of January 1, 20XX
Ohio | 3000000 | 60000 | 100000 | 30000 | 600000 | 3410000

## Drop-down lists (hidden)
State (short) | State (long) | Branch
AK | Alaska | Seattle
AL | Alabama | Atlanta
AR | Arkansas | Dallas
AZ | Arizona | San Francisco
CA | California | San Francisco
CO | Colorado | Denver
CT | Connecticut | Boston
DC | District of Columbia | Philadelphia
DE | Delaware | Philadelphia
FL | Florida | Atlanta
GA | Georgia | Atlanta
HI | Hawaii | San Francisco
IA | Iowa | Kansas City
ID | Idaho | Seattle
IL | Illinois | Chicago
IN | Indiana | Chicago
KS | Kansas | Kansas City
KY | Kentucky | Atlanta
LA | Louisiana | Dallas
MA | Massachusetts | Boston
MD | Maryland | Philadelphia
ME | Maine | Boston
MI | Michigan | Chicago
MN | Minnesota | Chicago
MO | Missouri | Kansas City
MS | Mississippi | Atlanta
MT | Montana | Denver
NC | North Carolina | Atlanta
ND | North Dakota | Denver
NE | Nebraska | Kansas City
NH | New Hampshire | Boston
NJ | New Jersey | New York
NM | New Mexico | Dallas
NV | Nevada | San Francisco
NY | New York | New York
OH | Ohio | Chicago
OK | Oklahoma | Dallas
OR | Oregon | Seattle
PA | Pennsylvania | Philadelphia
RI | Rhode Island | Boston
SC | South Carolina | Atlanta
SD | South Dakota | Denver
TN | Tennessee | Atlanta
TX | Texas | Dallas
UT | Utah | Denver
VA | Virginia | Philadelphia
VT | Vermont | Boston
WA | Washington | Seattle
WI | Wisconsin | Chicago
WV | West Virginia | Philadelphia
WY | Wyoming | Denver